## Source Onboarding Requests
AP Invoice Consolidation — New Source Onboarding Tracker
Owner: Sarah Chen (Finance Transformation PMO) ¦ Last updated: 2025-06-15 ¦ Status: In Progress
Request ID | Requested By | Date Submitted | Priority | Source System | ERP Platform | Region | Go-Live Target | Status | Notes / Open Items
SRC-2025-003 | Marcus Reinhardt (VP Manufacturing, EMEA) | 2025-04-12 | HIGH | Baan IV | Infor Baan | EMEA (Netherlands + UK sites) | Q3 2025 | Approved — mapping in progress | CFO approved 2025-04-20. Baan team contact: Karen van der Berg (karen.vdberg@corp.example). NOTE: Baan instance runs on-prem in Rotterdam DC. Data extract is CSV-based via nightly batch job to S3 landing zone. File arrives ~02:00 UTC. Karen confirmed GL codes follow GL-XXX pattern but cost center codes changed format in Jan 2025 (old: BC-XX, new: BC-XXX). Both formats may appear in historical data.
SRC-2025-004 | Jennifer Okafor (SVP Corporate Services, Americas) | 2025-05-03 | MEDIUM | Workday Financial Management | Workday | Americas (US + Canada) | Q3 2025 (after Baan) | Pending — data sharing agreement in legal review | Jennifer wants this live before Sept board meeting. Legal is reviewing the cross-entity data sharing agreement (DPA-2025-0041) — expected signoff by end of June. Workday connector already provisioned by IT (ticket INC-44291). IMPORTANT: Workday uses "In Review" status which is equivalent to our "PENDING". Also, Workday tenant WD-T2 is the London entity and invoices come through in GBP and EUR — make sure currency handling is consistent. Contact: Priya Sharma (priya.sharma@corp.example) for API access questions.
Historical context:
SAP (SRC-2025-001) and Oracle (SRC-2025-002) were onboarded in Q1 2025 and are currently live in the Silver layer. The standardized schema has 15 columns + SOURCE_SYSTEM. Any new source must map to this schema. See the 'Column Mapping Specifications' tab for detailed field-level mappings.
OPEN QUESTION: Do we need to carry forward Baan's BAN_COMPANY and Workday's WD_TENANT_ID into the Silver layer? These are system-specific identifiers with no equivalent in SAP/Oracle. Current recommendation: NO — drop them at the bronze-to-silver boundary. If we need them later, they're always available in the bronze tables. — Sarah, 2025-06-10

## Column Mapping Specifications
Field-Level Mapping: New Sources → Silver Standardized Schema
Prepared by: David Kim (Data Engineering) ¦ Reviewed by: Sarah Chen (PMO) ¦ v2.1 — 2025-06-14
BAAN IV — Source: BRONZE_BAAN_AP_INVOICES
Source Column | Source Type | Silver Target Column | Target Type | Required? | Transform | Business Rules / Notes | Status
BAN_INVOICE_ID | text (20) | INVOICE_ID | VARCHAR(20) | Yes | Direct map | Primary key in Baan. Format: BAN-NNN. | Confirmed
BAN_INVOICE_REF | text (30) | INVOICE_NUMBER | VARCHAR(30) | Yes | Direct map | This is the business-facing invoice number, NOT the internal ID. Use this for dedup. | Confirmed
BAN_VENDOR_CODE | text (15) | VENDOR_ID | VARCHAR(15) | Yes | Direct map | Format: BV-NNN. Karen confirmed these are stable and won't change. | Confirmed
BAN_VENDOR_DESC | text (100) | VENDOR_NAME | VARCHAR(100) | Yes | Direct map | May contain special chars (ü, é, etc.) from European vendor names. Ensure UTF-8. | Confirmed
BAN_INV_DATE | date | INVOICE_DATE | DATE | Yes | Direct map | Always in YYYY-MM-DD. No timezone issues. | Confirmed
BAN_PAY_DATE | date | DUE_DATE | DATE | Yes | Direct map |  | Confirmed
BAN_AMOUNT | number | INVOICE_AMOUNT | NUMBER(18,2) | Yes | Direct map | Always positive. Credit memos come as separate records with negative amounts — but Karen says they don't exist in current extract. Validate. | Confirmed
BAN_CURR | text (3) | CURRENCY_CODE | VARCHAR(3) | Yes | Direct map | Only EUR and GBP observed so far. No USD invoices from EMEA entities. | Confirmed
BAN_PAY_TERMS | text (20) | PAYMENT_TERMS | VARCHAR(20) | Yes | Normalize | Baan uses "N30", "N60" — standardize to match SAP format? SAP uses "NET30", "NET60". Decision: keep as-is for now, normalize in Gold layer. | Open — needs decision
BAN_PO_REF | text (20) | PO_NUMBER | VARCHAR(20) | No | Direct map | Optional. ~15% of Baan invoices have no PO (service invoices). | Confirmed
BAN_LINE_DESC | text (200) | LINE_DESCRIPTION | VARCHAR(200) | No | Direct map | Free text. Sometimes contains Dutch language descriptions. | Confirmed
BAN_GL_CODE | text (20) | GL_ACCOUNT | VARCHAR(20) | Yes | Direct map | Format: GL-NNN. Different from SAP (5100-10) and Oracle (A5100-40) formats. Do NOT attempt to cross-map at Silver layer. | Confirmed
BAN_COST_CTR | text (20) | COST_CENTER | VARCHAR(20) | Yes | Direct map | Format changed Jan 2025: old=BC-XX, new=BC-XXX. Both may appear. | Confirmed
BAN_STATUS | text (20) | APPROVAL_STATUS | VARCHAR(20) | Yes | Map values | POSTED→APPROVED, APPROVED→APPROVED, PENDING→PENDING. Baan doesn't have a "REJECTED" status — rejected invoices are deleted in Baan. | Confirmed
BAN_CREATED | timestamp | CREATED_AT | TIMESTAMP_NTZ | Yes | Direct map | UTC. Baan server is in CET but extract converts to UTC. | Confirmed
BAN_COMPANY | text (10) | — | — | No | DROP | Baan company code. Not needed in Silver. Available in Bronze if required for audit. | Confirmed — drop
WORKDAY FINANCIAL MANAGEMENT — Source: BRONZE_WORKDAY_AP_INVOICES
Source Column | Source Type | Silver Target Column | Target Type | Required? | Transform | Business Rules / Notes | Status
WD_INVOICE_ID | text (20) | INVOICE_ID | VARCHAR(20) | Yes | Direct map | Format: WD-NNN. | Confirmed
WD_INVOICE_NUM | text (30) | INVOICE_NUMBER | VARCHAR(30) | Yes | Direct map | Format: WD-AP-NNNNN. Business-facing number. | Confirmed
WD_SUPPLIER_ID | text (15) | VENDOR_ID | VARCHAR(15) | Yes | Direct map | Format: WS-NNN. Note: Workday calls them "suppliers", we standardize to "vendor". | Confirmed
WD_SUPPLIER_NAME | text (100) | VENDOR_NAME | VARCHAR(100) | Yes | Direct map | Clean data — no special char issues observed. | Confirmed
WD_INVOICE_DATE | date | INVOICE_DATE | DATE | Yes | Direct map |  | Confirmed
WD_DUE_DATE | date | DUE_DATE | DATE | Yes | Direct map |  | Confirmed
WD_AMOUNT | number | INVOICE_AMOUNT | NUMBER(18,2) | Yes | Direct map | Positive values only. Workday handles credits as separate "Credit Memo" document type — not in this extract. | Confirmed
WD_CURRENCY | text (3) | CURRENCY_CODE | VARCHAR(3) | Yes | Direct map | USD, GBP, EUR observed. USD is ~70% of volume. | Confirmed
WD_PAY_TERMS | text (20) | PAYMENT_TERMS | VARCHAR(20) | Yes | Normalize? | Workday uses "Net 30", "Net 60" (with space). SAP uses "NET30" (no space). Same question as Baan — keep as-is for now? | Open — needs decision
WD_PO_NUMBER | text (20) | PO_NUMBER | VARCHAR(20) | No | Direct map | Format: WPO-NNNN. Higher PO coverage than Baan (~90%). | Confirmed
WD_MEMO | text (200) | LINE_DESCRIPTION | VARCHAR(200) | No | Direct map | Workday calls it "Memo". Same purpose as LINE_DESCRIPTION. | Confirmed
WD_LEDGER_ACCOUNT | text (20) | GL_ACCOUNT | VARCHAR(20) | Yes | Direct map | Format: LA-NNNN. Different from all other systems. Do NOT cross-map. | Confirmed
WD_COST_CENTER | text (20) | COST_CENTER | VARCHAR(20) | Yes | Direct map | Format: WCC-XXXX. Consistent format. | Confirmed
WD_APPROVAL_STATUS | text (20) | APPROVAL_STATUS | VARCHAR(20) | Yes | Map values | Approved→APPROVED, In Review→PENDING. Workday also has "Denied" but those don't appear in the AP extract (filtered upstream). | Confirmed
WD_CREATED_DATE | timestamp | CREATED_AT | TIMESTAMP_NTZ | Yes | Direct map | UTC. Workday cloud — no timezone conversion needed. | Confirmed
WD_TENANT_ID | text (10) | — | — | No | DROP | WD-T1=US, WD-T2=London. Not needed in Silver. Region can be inferred from currency if needed. | Confirmed — drop

## Business Rules & Exceptions
Business Rules, Exceptions & Open Items
Compiled from stakeholder interviews and source system documentation. Last updated: 2025-06-14.
Rule ID | Category | Rule Description | Decision / Owner
BR-001 | Status Normalization | Each source system uses different approval status values: • SAP: APPROVED, PENDING (already matches Silver) • Oracle: VALIDATED→APPROVED, APPROVED→APPROVED, PENDING→PENDING • Baan: POSTED→APPROVED, APPROVED→APPROVED, PENDING→PENDING • Workday: Approved→APPROVED, In Review→PENDING Map all variants to the Silver standard: APPROVED or PENDING. No other status values should reach the Silver layer. | Confirmed by Sarah Chen, 2025-05-20. Implement as CASE statement in Silver DT.
BR-002 | Currency Handling | Baan invoices are denominated in EUR and GBP only (EMEA entities). Workday is primarily USD (~70%) with some GBP and EUR from the London tenant. SAP is mixed. Oracle is primarily USD. Do NOT convert currencies at the Silver layer. Silver stores the original transaction currency. Currency conversion happens in Gold (if needed) using the corporate FX rate table maintained by Treasury. | Confirmed by Marcus Reinhardt (Baan) and Jennifer Okafor (Workday). Treasury FX table is out of scope for this project.
BR-003 | Duplicate Detection | Baan has a known issue: the nightly extract sometimes sends the same invoice twice with different BAN_INVOICE_ID values but identical BAN_INVOICE_REF. This happens when an invoice is modified after the extract window opens. Recommendation: Deduplicate on INVOICE_NUMBER (mapped from BAN_INVOICE_REF) using the latest BAN_CREATED timestamp. The Silver DT should handle this with a QUALIFY ROW_NUMBER() OVER (PARTITION BY INVOICE_NUMBER ORDER BY CREATED_AT DESC) = 1. | Reported by Karen van der Berg, 2025-05-15. Engineering to implement. NOTE: This is a Silver-layer concern, not Bronze.
BR-004 | Data Quality — Amount Thresholds | Flag invoices with INVOICE_AMOUNT > $500,000 USD equivalent for manual review. These are typically data entry errors (extra zero) or should be split across multiple cost centers. This is NOT a filter — do not drop these rows. Add a data quality check that alerts when the count of high-value invoices exceeds expectations. | Requested by Finance Controller (Tom Walsh), 2025-06-01. Implement as a DMF in the Guardrails Pack, not in the Silver DT itself.
BR-005 | Payment Terms Normalization | Inconsistent formatting across systems: • SAP: "NET30", "NET60" (no space, uppercase) • Oracle: "N30", "N60" (abbreviated) • Baan: "N30", "N60" (same as Oracle) • Workday: "Net 30", "Net 60" (space, mixed case) OPEN QUESTION: Normalize at Silver layer or Gold layer? If Silver, use SAP format (NET30, NET60) as the standard since SAP was the first source. | NEEDS DECISION — Sarah to discuss with David Kim by 2025-06-20. Current recommendation: leave as-is at Silver, normalize at Gold.
BR-006 | GL Account Cross-Reference | Every source system uses a different GL account numbering scheme: • SAP: 5100-10, 6200-10 (NNNN-NN) • Oracle: A5100-40, A6200-20 (ANNNN-NN) • Baan: GL-510, GL-620 (GL-NNN) • Workday: LA-6200, LA-6800 (LA-NNNN) Do NOT attempt to create a unified chart of accounts at the Silver layer. This requires a master data mapping table maintained by Accounting. Silver stores the original GL code as-is. Gold layer will join to the CoA mapping table (future phase). | Confirmed by Tom Walsh and Sarah Chen. CoA mapping is Phase 2 (Q4 2025).
BR-007 | Source System Identifier | Every row in the Silver layer must include a SOURCE_SYSTEM column with values: • 'SAP' for BRONZE_SAP_AP_INVOICES • 'ORACLE' for BRONZE_ORACLE_AP_INVOICES • 'BAAN' for BRONZE_BAAN_AP_INVOICES • 'WORKDAY' for BRONZE_WORKDAY_AP_INVOICES This is a hard-coded literal in each UNION ALL branch, not derived from the data. | Established pattern from Phase 1 (SAP/Oracle). Continue for new sources.
BR-008 | System-Specific Columns | Each source has columns that don't exist in other systems: • SAP: SAP_COMPANY_CODE, SAP_DOCUMENT_TYPE • Oracle: ORACLE_ORG_ID, ORACLE_SOURCE • Baan: BAN_COMPANY • Workday: WD_TENANT_ID These are dropped at the bronze-to-silver boundary. If analytics needs them, join back to the bronze table using INVOICE_ID + SOURCE_SYSTEM. | Confirmed by David Kim, 2025-06-10. See also the open question in the Onboarding tab.
BR-009 | Refresh Timing | Source data arrives at different times: • SAP: Real-time CDC via Kafka (already in Snowflake) • Oracle: Hourly batch extract • Baan: Nightly batch (~02:00 UTC) • Workday: Hourly via Workday connector The Silver DT uses TARGET_LAG = DOWNSTREAM, meaning it refreshes only when downstream consumers need it. For the Gold DT, TARGET_LAG should balance freshness against credit consumption. Proposed: 2 hours for now, revisit after 30 days of monitoring. | Engineering decision. Marcus wants near-real-time for Baan but acknowledges the nightly batch is the constraint. No action needed — DT handles this.
BR-010 | Data Retention | Bronze tables retain all historical data (no purge). Silver and Gold are current-state views (Dynamic Tables). For historical analysis, query Bronze directly or create a separate time-series table. Out of scope for this project but flagging for Phase 2 planning. | Noted by Sarah Chen, 2025-06-12. Add to Phase 2 backlog.